Scope of Work

Project 5: Analysis of Total Coliform Rule (TCR) Violations Across Five U.S. States

Team Members: Savanna Flores, Dawa Tamang, Rebecca Carroll

Course: CIVE 202 – Civil Engineering Analysis II

Client: UMass Amherst Water Research Team

Date Submitted: 02/27/2026

Project Goals

The goal of this project is to analyse Total Coliform Rule (TCR) violations in public drinking water systems across five U.S. states Georgia, Texas, Ohio, Massachusetts, and Washington using the Safe Drinking Water Information System (SDWIS) database. The client has requested two primary analyses:

- A summary table or figure showing TCR violations by state over time and

- An investigation of whether small water systems experience more TCR violations than larger systems.

The project will quantify temporal and spatial patterns in TCR violations and evaluate differences by system size category. In addition to quantitative analysis, the team will provide a written discussion interpreting observed differences across states and between small and large systems. The final deliverables will be prepared for use by a research team examining microbial drinking water quality compliance.

Project Tasks

Our team will complete the following tasks:

Task 1: Data Extraction and Cleaning from SDWIS

Our team members will download TCR violation data for Georgia, Texas, Ohio, Massachusetts, and Washington from the SDWIS Federal Reporting Services portal. The dataset will be filtered to include only Total Coliform Rule violations and active public water systems. Data will be cleaned in Excel by removing unwanted columns formatting date fields, and retaining key variables including state, population served, water source type (groundwater vs. surface water), violation type, and compliance period dates. Our team will prepare a cleaned CSV file for Python analysis.

Task 2: Data Analysis and Visualization in Python

We will use python for data analysis using the pandas and NumPy libraries. The team will group and aggregate TCR violations by state and year to summarize trends over time. Violations will also be summarized by system size category, derived from population served, to compare small and large water systems.

Task 3: Interpretation and Written Reporting

The team will interpret the analytical results and prepare a written discussion addressing differences in TCR violations across states and between small and large systems. Team members will review external resources, including EPA documentation on the Total Coliform Rule and peer reviewed studies on drinking water compliance challenge to support explanations of observed patterns.

Project Deliverables

The following deliverables will be provided to the client by the project due date:

| Deliverable | Description | Due Date |
| --- | --- | --- |
| Raw SDWIS Data File | Original violation report exported from SDWIS | 04/27/2026 |
| Cleaned CSV Dataset | Cleaned and formatted dataset ready for Python analysis | 04/27/2026 |
| Python Code File | Python notebook used for data processing and visualization | 04/27/2026 |
| Annotated Code Document | Explanation of Python code steps | 04/27/2026 |
| Summary Tables & Figures | Tables and figures showing TCR trends by state and system size | 04/27/2026 |
| Gantt Chart | Timeline of project activities | 04/27/2026 |
| GitHub Repository Link | Repository containing code and data files | 04/27/2026 |
| Final Written Report | Report summarizing methods, results, and interpretation | 04/27/2026 |